## Sheet1
S/No | Resource Name | Task | Sub Task | Demo | Screenshots | Cleanup | Done | Date
1 | Srinivas | Mobile App-1 | Menu Options, Highlights, iOS, Android, Log Off, Native Search, Floating Action | Done |  |  |  | 2020-06-15
2 | Mounika | Portals-2 | Patient, Doctor and Care Worker. Menu Options | Done |  |  |  | 2020-06-15
3 | Mounika | My Profile(Desktop/Mobile)-3 | Desktop/Mobile |  |  |  |  | 2020-06-17
4 | Vikram | My Documents and Pulse | Desktop/Mobile | Done |  |  |  | 2020-06-15
5 | Madhuri | Patient Registration | End to end patient registration including emails. | Done |  |  |  | 2020-06-15
6 | Srinivas | My Appointments(Desktop/Mobile)-6 | Desktop and mobile |  |  |  |  | 2020-06-16
7 | Aparna | My Prescriptions-7 | Desktop | Done |  |  |  | 2020-06-16
8 | Madhuri | Personalized Notifications (Push/Portal) | Prescriptions - Mobile/Desktop | Done |  |  |  | 2020-06-16
9 | Vikram | Appointment Booking/Consultation | Desktop/Mobile | Done |  |  |  | 2020-06-16
10 | Aparna | Appointment Cancellation/Reschedule | Desktop/Mobile |  |  |  |  | 2020-06-17
11 | Vikram | Push Notifications (Appointment/Prescription) | Desktop/Mobile |  |  |  |  | 2020-06-17
12 | Mounika | Dashboards | Desktop/Mobile |  |  |  |  | 2020-06-18
13 | Vikram | Deployment / Appointment Push Notification | Desktop/Mobile |  |  |  |  | 2020-06-17
14 | Vikram | Certificates, Logins, Splash Screens | Pega Mobile |  |  |  |  | 2020-06-18
15 | Aparna | Appointment Notifications | Desktop/Mobile |  |  |  |  | 2020-06-18
16 | Madhuri | Send Prescription Notifications | Daily(All scenarios) - Desktop/ Mobile | Done
17 | Madhuri | Upcoming Appointments of Healthcare Worker | New Reports and KPIs |  |  |  |  | 2020-06-18
18 | Madhuri | Notify Case Workworker to add a space | Just as a notification or a pulse task. | Not needed
19 | Srinivas | Prescription (Mobile) and Offline Mobile | Filter/Cancel mobile prescription
20 | Srinivas | Webchatbot for appointment process | Nizam will do design and initial coding
21 | Nizam | Maps integration and opening mobile actions | Mobile App with actions
22 | Nizam | AI Model for No Show calculation | Appointment case and all AI predictors
23 | Nizam | Pitch Video with voice over | HD 5 minutes video with a demo.
24 | Nizam | Documentation and Slide | Final presentation deck